## Slide 1: What you need to know about Local Public Authority (LPA) owned projects

## Slide 2: General comments:
These projects are locally owned and the LPA should be involved and informed throughout the project.
The project agreement is between KDOT and the LPA, not the consultant. If there are issues, it is the LPA’s responsibility.
Communication with the BLP Project Manager should be often and honest. Don’t tell us what we want to hear.
Plans should follow KDOT format…more or less. If you aren’t sure about how critical the format is for something…ask!
KDOT Bid items must be used for KDOT let projects. KDOT must approve all specifications for LPA administered projects.
The project plans are supporting documents for the Uniform Relocation Act on Federal and State Aid projects. Appropriate Land Surveying requirements must be followed, and complete references must be included.

## Slide 3: Project Schedule (RUPIS)

## Slide 4: Project Schedule (RUPIS)
Rural
Urban
Project
Implementation
Schedule

## Slide 5: This is a guide…

## Slide 6: This is a guide…
If at any point the project is behind schedule enough to cause concern, it is up to the LPA (the project Owner) and their consultant to propose a way to get back on schedule. Moving the let date should be a last resort.
If at any point there is a detailed estimate that shows a cost increase near or over 25% difference to the original or previous cost estimate, contact KDOT (and the MPO, if the project is located in an MPO) right away. The Program Manager may need to check to see if additional funds are available and the TIP and/or STIP will require modification prior to obligation.

## Slide 7
LPA should NOT wait for project agreement to start Consultant acquisition or design UNLESS there are State or Federal Funds in the Design Phase.
If the LPA wants the Design Consultant to do Construction Inspection they should follow QBS process and include both phases. This MUST have KDOT oversight if State or Federal Funds are used in either phase.
Make sure required language (dependent on funding type) is included in agreement. Contact KDOT-BLP if you are unsure of what is needed.

## Slide 8
Plans should be approximately 50% complete (bridge portion approximately 25% complete)
Should include:
  Title Sheet
  Plan/Profile Sheets (Including worst case ROW limits)
  Bridge Plan and Construction Layout sheets
  Traffic Control and Phasing
  Preliminary cross sections

## Slide 9
After Field Check but before Office Check
  KDOT should complete NEPA review and issue Environmental Clearance Statement
    Exception would be if additional detailed study or mitigation must be performed by LPA
  KDOT should issue Design Summary Document (DSD)
  KDOT should provide required forms and procedures to begin ROW acquisition process to LPA
  LPA should begin ROW acquisition and Utility Relocation Coordination
    REMEMBER-All persons directly involved in ROW acquisition MUST be certified through the ROWCP (http://kutc.ku.edu/training-webinars#)
  Consultant should determine what permits are required and begin permit application process.

## Slide 10
Plans should be 100% complete
  The consultant should believe that the plans are ready for PSE before submitting to KDOT.
Detailed Estimate
Form 1307 (Status of Permits)
Geology Report if project includes a bridge
ROW acquisition and Utility Relocation process should be well under way by this point.

## Slide 11
Plans should be 100% complete
  ALL markups from Office Check addressed.
  If no additional comments, the KDOT Project Manager may elect to upgrade to PSE set.
Detailed Estimate
Form 1307 (Status of Permits)
ROW acquisition and Utility Relocation process should be nearly complete or complete.

## Slide 12
Plans should be 100% complete
  ALL markups from Final Check addressed.
Detailed Estimate
Form 1307 (Status of Permits) and copies of all permits
Forms 1304 and 1306 - ROW acquisition and Utility Relocation process must be complete.

## Slide 13
Plans should be 100% complete
  ALL markups from PSE Check addressed.
KDOT will NOT review this set! Consultant is responsible for addressing all PSE comments.
KDOT cannot advertise without CE agreement completed!

## Slide 14: After Project Letting…
Bid Letting is broadcast at https://www.ksdot.org/bureaus/burconsmain/audio.asp
KDOT will call for “verbal commitment” followed up with email containing “Commitment of Funds” documents to be signed by LPA
  Must be signed and returned to KDOT within 23 days of letting
  Funds must be received by KDOT by date noted on “Commitment of Funds” document

## Slide 15: Questions?