## Read Me
Instructions:
Please use this form to submit Payment Requests to the Bureau of Local Projects.
To create a new tab for each pay request:
1.) | Go to the most recent "PR#nn" tab.
2.) | Press and hold "CTRL", click the current "PR#nn" tab with the mouse and drag to the right.
3.) | Double Click with mouse on the new tab and rename as appropriate. (PR#02, PR#03, etc.)
Light gray highlighted fields are for user input. All other fields will be computed and are locked.
+++++ Be sure to include invoicing details and 1010 forms with your submittal. +++++
A completed "Example" is included.
If you have any questions about this form, please contact Bill Legge at (785) 368-7397, wlegge@ksdot.org
Revision History:
| Rev01: | Added "Enter as a negative number." comments for "Less: …." cells.
| Rev02: | Changed title from "Payment Request" to "Payment Request Form".
Renamed "Contract Max" to "Project Max". This is used for over the max computation.
Added "Reimbursement Max" line to match agreement terminology. This is FYI.
Added DOT Form number to footer. (Number yet to be assigned.)
| Rev03: | Adjusted and renamed fields to aid input into CMS.
Changed "Less: Over the Max…." computation.
Added revision date and DOT Form number 1313 to footer.
Added conditional checks to compute CE funding availablity.
| Rev04: | Added 2 CFR Part 200 language and signature block
| Rev05: | Added additional adjustment lines
Revised CE Reimbursement line
Added "Contract Amount" field
Added "Must enter Begin and End dates!" warning
Added "LPA Invoice #" warning
Added alternative for entering a fixed local retainage amount
Yes
No
Less: Liquidated Damages
Plus: Incentive

## Example
Payment Request Form
Date: |  |  | 2015-09-15
Project Description: |  |  | Geometric Improvements at Yellow Brick Road and Acme Street
KDOT Project #: |  |  | 106 N-5555-01
CMS Contract #: |  |  | 01716nnnn
LPA Project #: |  |  | TOTO123
Contract Amount: |  |  | 215000
Project Max: |  |  | 200000
Reimbursement Max: |  |  | 160000 |  |  |  | to the LPA
LPA: |  |  | Emerald City
LPA Invoice #: |  |  | 20150002
Work completed through: |  |  |  | Begin Date: |  |  | 2015-08-01 | End Date: |  | 2015-08-31
Final Invoice ? |  |  |  | No | FALSE
Total Costs Claimed | [10 empty] | 245000
Less: | Non-Participating | [9 empty] | -15000
0
0
Less: | Local Retainage |  |  |  |  | or Fixed Amount of |  | 1000 |  |  | -1000
Subtotal | [10 empty] | 229000
Less: | Over the Max of the Contract | [9 empty] | -30000
Total Participating Cost | [10 empty] | 199000
KDOT/Federal Participation |  |  |  | 80% | [6 empty] | 159200
Less: | Local Participation |  |  | 20% |  | Prepaid Amount |  |  |  |  | -39800
Less: | KDOT Retainage | [9 empty] | -500
Less: | Previous Reimbursements | [9 empty] | -99500
AMOUNT DUE | [10 empty] | 59200
Previous Payments from KDOT | [10 empty] | 99500
Plus: Current Reimbursement from KDOT | [10 empty] | 59200
Total Reimbursement from KDOT | [10 empty] | 158700
Outstanding Reimbursements from KDOT | [10 empty] | 500
Total Reimbursement for CMS contract including pending payments | [10 empty] | 159200
*** Note: Invoice details must be submitted with invoice.***
By Signing this report, I certify to the best of my knowledge and belief that the report is true, accurate and the expenditures are for the purposes and objectives set forth in the terms and conditions of the Federal award. I am aware that any false, fictitious, or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise.
Certified by: | [8 empty] | Attest:
The Wizard of Oz | [8 empty] | Good Witch of the North
Note on F6: This will be provided to you by your KDOT PM.
Note on F7: If the LPA has assigned their own project number, enter it here or leave blank.
Note on F8: You will need to keep this up-to-date if any change orders are processed.
Note on G14: Select "Yes" or "No".
Note on S17: Enter as a Negative number.
Note on S26: Enter as a Negative number.
Note on S27: Enter as a Negative number.
Note on S35: Must have a Project Max AND be Final Invoice AND Local Retainage must be 0% to compute and display.
Note on A43: Change "Title1" as appropriate to person that has authority to make binding decisions for the LPA.
Note on N43: Change "Title2" as appropriate.

## PR01
Payment Request Form
Date:
Project Description:
KDOT Project #:
CMS Contract #:
LPA Project #:
Contract Amount:
Project Max:
Reimbursement Max: |  |  | 0 |  |  |  | to the LPA
LPA:
LPA Invoice #: | [6 empty] | Please enter an Invoice Number!
Work completed through: |  |  |  | Begin Date: |  |  |  | End Date:
Final Invoice ? |  |  |  | No | FALSE |  | Must enter Begin and End dates!
Total Costs Claimed | [9 empty] | 0
Less: | Non-Participating | [8 empty] | 0
0
0
Less: | Local Retainage |  |  | 0% |  | or Fixed Amount of |  |  |  | 0
Subtotal | [9 empty] | 0
Less: | Over the Max of the Contract | [8 empty] | 0
Total Participating Cost | [9 empty] | 0
KDOT/Federal Participation |  |  |  | 80% | [5 empty] | 0
Less: | Local Participation |  |  | 20% |  | Prepaid Amount |  |  |  | 0
Less: | KDOT Retainage | [8 empty] | -500
Less: | Previous Reimbursements | [8 empty] | 0
AMOUNT DUE | [9 empty] | -500
Previous Payments from KDOT | [9 empty] | 0
Plus: Current Reimbursement from KDOT | [9 empty] | -500
Total Reimbursement from KDOT | [9 empty] | -500
Outstanding Reimbursements from KDOT | [9 empty] | 500
Total Reimbursement for CMS contract including pending payments | [9 empty] | 0
*** Note: Invoice details must be submitted with invoice.***
By Signing this report, I certify to the best of my knowledge and belief that the report is true, accurate and the expenditures are for the purposes and objectives set forth in the terms and conditions of the Federal award. I am aware that any false, fictitious, or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise.
Certified by: | [8 empty] | Attest:
Title1 | [8 empty] | Title2
Note on F6: This will be provided to you by your KDOT PM.
Note on F7: If the LPA has assigned their own project number, enter it here or leave blank.
Note on F8: You will need to keep this up-to-date if any change orders are processed.
Note on G14: Select "Yes" or "No".
Note on S17: Enter as a Negative number.
Note on G20: For the % calculation to work, the Fixed Amount field must be blank.
Note on S20: For the % calculation to work, the Fixed Amount field must be blank.
Note on S26: Enter as a Negative number.
Note on S27: Enter as a Negative number.
Note on S35: Must have a Project Max AND be Final Invoice AND Local Retainage must be 0% to compute and display.
Note on A43: Change "Title1" as appropriate to person that has authority to make binding decisions for the LPA.
Note on N43: Change "Title2" as appropriate.